WESTERN PACIFIC UNIVERSITY

CMN224 / CMP224 Software Engineering — Week 3

# Lab 3: Lifecycle Selection & Increment Plan

Formative (ungraded) · Moodle-enabled · output feeds Task 2 Part 2 directly

| Item | Details |
| --- | --- |
| Linked to | Week 3 lecture — Software Process Models (ULO2, ULO3) |
| Work mode | Individually, on the SAME client scenario you chose for Task 2 |
| Time | About 90 minutes |
| Submission | Completed worksheet uploaded to Moodle AND committed to week03/ in your Git portfolio |
| Why it matters | Section C of this worksheet is the first draft of Task 2 section 2.3 (work schedule). Do it properly now and Week 8 gets much easier. |

## Purpose

In the lecture you met six ways to organize the same four activities, and six questions that decide which one fits. Now you apply that decision to a real client — yours. There is no single correct model; the marks in Task 2 (and the exams) come from the quality of your justification.

## Part A — Apply the six selection questions (30 min)

For each question, answer for YOUR client scenario (Kina Ridge Primary School or Waghi Valley Produce Cooperative) and say what it pushes you toward.

| # | Selection question | Your answer for this client | Pushes toward… |
| --- | --- | --- | --- |
| 1 | How well understood are the requirements? | The basic requirements are fairly clear. These are the requirements that the client requires; offline recording of produce, management of the members, payment tracking, price control. However, there are still some requirements that still need to be clarified regarding payment disputes and reporting. | Iterative agile approach to allow requirements to be refined during development. |
| 2 | Can the client engage continuously? | Yes, the manager, depot clerk, and committee representatives are available to provide feedback throughout the project. | Agile development with regular reviews and feedback. |
| 3 | What does the contract or funding demand? | There is no clarification of a contract or funding from the government. The focus is on delivering a working system that solves the operation problem. | Agile or Hybrid approach. |
| 4 | How big is the team, and where is it? | The project is developed by a small team with stakeholders located at the cooperative located in Mt. Hagen. | Agile/Scrum because communication is between small teams which makes it easier to adapt. |
| 5 | What is the cost of failure? | Failure can lead to payment disputes, loss of trust, financial inaccuracy, and loss of members records. | Careful iterative development with testing to reduce operational risks. |
| 6 | How fast must value appear for this client? | The manager wants to reduce records loss and disputes ASAP. Delivering useful features quickly would provide immediate benefits. | Agile with increment releases so values appear easily. |

## Part B — Choose and justify (15 min)

Chosen lifecycle: Agile (Increment Development) with milestone reviews for management and the member committee (hybrid approach).

In 150–200 words, justify the choice using your Part A answers. Name at least one factor that argues AGAINST your choice, and say how you will manage it.

The most suitable life cycle for the Waghi Valley Produce Cooperative will be an agile approach with incremental delivery and formal milestone reviews. The requirements are understandable because they needed offline produce recording, member management, payment tracking, and price control. However, some requirements mostly around the disputes of payments, reporting, and record management will be more clarified when the users start using the system. Agile supports this by allowing the features to be developed and improved through regular feedback.

Frequent practical reviews can be done by the client by engaging with the manager, depot clerk, and the committee members. The Agile method is used because it aligns well with the project in the manner that it involves a small development team. In addition, the cooperation also wants quick values, so core deliveries such as produce intake recording and early receipt printing will be more beneficial and will reduce record losses and payment disputes.

A factor that is affecting Agile is the unreliable internet connectivity and limited technology resources at the depot. It is difficult for the depot to be online regularly. This risk can be managed by conducting scheduled face-to-face reviews, using offline demonstrations, and documenting key decisions during milestone meetings. Combining Agile development with formal milestone reports ensures flexibility while still providing accountability and oversight for cooperative management and the committee.

Blends are professional, not a cop-out. "Incremental delivery internally, phase milestones reported to the board" is a legitimate and common answer in PNG work — provided you explain how the two fit together.

## Part C — Plan three increments (35 min)

Split your client's system into three increments. Increment 1 must be genuinely usable on its own — something the client could put to work the day you hand it over.

| Increment | What it delivers | Why THIS order (risk or value?) | Rough duration & why |
| --- | --- | --- | --- |
| 1 | Offline produce intake system, members database, daily price sheets, receipt/acknowledgement printing, secure user login for manager and depot clerk. | Highest business value. This immediately replaces the carbon- copy books and reduces lost records and disputes. The cooperative can start using it as soon as it is delivered. | 4weeks because these are the core functions needed daily depot operations and require thorough testing offline. |
| 2 | Fortnight payment calculations, payment summaries, deduction management, payment history records, and dispute logging. | Reduces financial disputes and improves transparency. Builds on the intake records captured in increment 1. | 3 weeks because payment function depends on the accurate intake data already allocated by the first increment. |
| 3 | Management reports, member delivery history reports backup and recover tools, audit logs, and data exports/synchronization when connectivity is available. | Lower immediate but important for long-term management and accountability. Also reduces risk of data loss. | 3 weeks because reporting and backup features require data generated by earlier incremements. |

### C4. Delivery-condition check

For each increment, note one PNG delivery condition that affects when or how you can deliver it (client travel, power, connectivity, harvest or school-term timing, committee approval cycles).

Condition notes

Increment 1 (Unreliable power supply (solar and generator))- limited internet connectivity means all increments must be installable and testable offline.

Increment 2 (Fortnight payment cycle)- committee approval cycles may influence when payment and reporting features can go live.

Increment 3 (Member committee approval and meeting schedules)- travel to the depot near Mt. Hagen may affect training and deployment schedules

## Part D — Reflect (10 min)

- If the client suddenly demanded ALL three increments by the same original deadline, which corner of the dependency triangle would you push back on, and what exactly would you say to them?

- Which of your three increments is most likely to change after the client sees increment 1? What does that tell you about how firmly to specify it now?

Your answers

I would push back on the scope corner of the dependency triangle. If the deadline and budget remain unchanged, it is unrealistic to deliver all planned features at the same level of quality. “We can meet the original deadline, but we cannot safely deliver all three increments without increasing either time or resources. To maintain system quality and reliability, I recommend prioritizing the most critical features such as offline produce recording, member records, payment calculations, and receipt generation. Less critical features like advanced reports, audit logs, and data synchronization can be delivered in a later release. This ensures the cooperative receives a usable and reliable system on time while reducing the risk of errors and project failure.”

Increment 2 (Payment management and dispute handling) Once depot staff start recording produce electronically, they may discover new requirements for payment calculations, deductions, dispute resolution, or member payment reports. Real world usage often reveals the processes that were not fully understood during the initial requirement gathering. This tells me that increment 2 should be specified at a high level initially, but not in excessive detail. The core objective should be documented, while leaving flexibility to refine requirements based on feedback from users after they have gained experience with increment 1. This supports the Agile approach and reduces the risk of building payment features that do not match the cooperative’s actual needs.

## Submitting

- Save as Lab3_<YourName>.docx and upload to Moodle → Week 3 → Lab 3.

- Copy it into week03/ in your portfolio and commit:

git add week03/ && git commit -m "Add Lab 3 lifecycle selection and increment plan"

- Keep it open when you start Task 2 Part 2 — Parts B and C become sections 2.3 and 2.4.